## SUMMER HUBS - RECOVERY PLAN
Create a project schedule in this worksheet. Enter the title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook, is in the About worksheet. Continue navigating down column A to hear further instructions. | COMMUNITY HUBS : COVID-19 Operational & Delivery Plan
Enter the company name in cell B2. | Version: v4
Enter the name of the project lead in cell B3. Enter the project start date in cell E3. The project start label is in cell C3. | Issue Date: 16/06/2020 | Recovery Phase Start: |  |  |  | 2020-06-16
The display week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is automatically calculated. There are 8 weeks represented in this view from cell I4 to cell BF4. You should not modify these cells. The display week label is in cell C4. | Document Controller: Graeme Morrison
Cells I5 to BL5 contain the day number for the week represented in the cell block above each date cell and are automatically calculated. You should not modify these cells. Today’s date is outlined in red (hex #AD3815) from today’s date on row 5 throughout the entire date column to the end of the project schedule.
This row contains headers for the project schedule that follows below them. Navigate from B6 to BL6 to hear the content. The first letter of each day of the week for the date above that heading starts in cell I6 and continues to cell BL6. All project timeline graphing is automatically generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | NOTE | ASSIGNED TO | PRIORITY (RAG) | PROGRESS | START | END | DAYS
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cell B8 contains the phase 1 sample title. Enter a new title in cell B8. Enter a name to assign the phase to, if this applies to your project, in cell C8. Enter the progress for the entire phase, if this applies to your project, in cell D8. Enter the start and end dates for the entire phase, if this applies to your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | VENUE HUBS - PRE-OPENING PHASE - Operational Planning
| Establish an effective and functional operational Guidance to support safe provision of NLC's Community Hubs with the reopening of the venue and specific activity areas; Main Sports Halls, Small, Medium & Large studios and outdoor activity areas including sports pitches and athletics tracks only, and continue with the secure closure on lockdown of all areas not in use including gym and wetside facilities. This program will operate from the 25th of June until the 10th of August 2020 and may be subject to change based on the guidelines directed by the Scottish Government | C&LNL will deliver programmed sports activities and structures across the 9 community hubs. This would be coordinated and managed by the Operational Sport Development Team across the 6 weeks of the summer holidays. These activities are aimed at all ages and abilities from P1-S6 and will be delivered by qualified sports coaches who have a range of experience from coaching at sport specific coaching programmes, holiday programmes and diversionary projects. The hubs will operate from am & pm and the shift pattern would be split into the following hours; 9am-5pm– Monday to Friday 10am-3pm – Saturday & Sunday | Operations | 1 | 90% | 2020-05-08 | 2020-06-25 | 49
| Develop COVID-19 recovery plans for the identified community hub venues | • Broadwood Stadium • Airdrie Sports Centre • Sir Mat Busby • Ravenscraig Sports Facility • Wishaw Sports Facility • Shotts Sports Centre • Ian Nicholson Centre | Operations | 1 | 100% | 2020-06-09 | 2020-06-16 | 8
Rows 10 to 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 to A13 or go to cell A14 to learn more. | Reinstate building plant; heating air conditioning |  | Estates & Health & Safety | 1 | 100% | 2020-06-16 | 2020-06-25 | 10
| Reinstate front of house ITC systems; |  | IT | 1 | 100% | 2020-06-16 | 2020-06-25 | 10
| Identify new phase pricing strategy and Financial planning |  | Operations | 1 | 100% | 2020-06-16 | 2020-06-25 | 10
| Re-establish a telephone lines and MRM booking system for each respective venue | One main telephone lines to be re-established per venue along with associated MRM and payment systems. | Operations | 1 | 100% | 2020-06-16 | 2020-06-25 | 10
| Re-establish one FOH personal per venue as per Community hub operating hours. Establish a COVID-19 safe working in that environment to accommodate one reception staff. | All safe distancing, staff well-being & safety measures must be implemented. Forlough and HR implications along with shift rotas and operating hours must also be considered. All front of house reception areas must be clear of all unnecessary items, documents, leaflets, stationery to allow for easy sanitisation all hard surfaces. | Operations | 1 | 50% | 2020-06-16 | 2020-06-25 | 10
| Update IT MRM booking system to accommodate community hubs | Review booking screens and POS. | Sports development | 1 | 100% | 2020-06-16 | 2020-06-25 | 10
| All self-service kiosk and turnstiles have to remain closed during this phase | All hard surface touch points should be kept to an absolute minimum | Operations | 1 | 100% | 2020-06-16 | 2020-06-25 | 10
| Pre opening deep cleaning and disinfectant plan; all key touch points. |  | Operations | 1 | 50% | 2020-06-16 | 2020-06-25 | 10
| Install FOH - Reception temporary Perspex shields | Liaise with our respective venue management to identify the most appropriate and practical front of house solution. | Operations | 1 | 50% | 2020-06-16 | 2020-06-25 | 10
| Ensure all cleaning and disinfecting stock levels | Disinfecting and sanitising chemicals | Operations | 1 | 50% | 2020-06-16 | 2020-06-25 | 10
| Ensure all PPE personals and sanitising equipment | Cleaning, equipment, staff uniforms, PPE | Operations | 1 | 50% | 2020-06-16 | 2020-06-25 | 10
| Develop & deploy COVID-19 signage stratagy | Develop venue specific COVID-19 signage strategies and plans. Prepare venue layouts detailing the locations and type of signage required. | Operations | 1 | 50% | 2020-06-16 | 2020-06-25 | 10
| Review Venue Opening hours to support the community hubs. | Single shift arrangements | Operations | 1 | 100% | 2020-06-16 | 2020-06-25 | 10
| Review and re establish service contracts | Biffa, PHS, Cryo Service, G4S | Operations | 1 | 50% | 2020-06-16 | 2020-06-25 | 10
| 2m lines marked for waiting areas out side the building | Ensure social distancing rules are enforced | Operations | 1 | 50% | 2020-06-16 | 2020-06-25 | 10
| Close all changing facilities and restrict the number of public toilet facilities | Customers staff must arrive 'Activity Ready'. Staff and customer toilet facilities should be controled to mange one users at any one time. Strict cleaning/ disinfectant regime must be in place after use. | Operations | 1 | 100% | 2020-05-08 | 2020-06-25 | 49
| Remove all public seating / waiting areas | When practical to do so implement one-way systems for customers | Operations | 1 | 100% | 2020-05-08 | 2020-06-25 | 49
| Public catering and vending facilities | All catering units and vending facilities to remain closed until the appropriate change to lockdown guidelines is advised by the Scottish government | Catering | 1 | 100% | 2020-08-11 | 2020-08-11 | 1
| Initial site venue maintenance survey/inspections | Site Visit and determine any defects and report | Estates & Health & Safety | 1 | 100% | 2020-06-16 | 2020-06-25 | 10
| Water Hygiene: Carry out building legionella treatments and checks | High Risk to staff. Needs RA. Review current advice and implement. IWS to cost | Estates & Health & Safety | 1 | 90% | 2020-06-16 | 2020-06-25 | 10
| Statutory Inspections | Venue Managers to advise/arrange outstanding items | Estates & Health & Safety | 1 | 90% | 2020-06-16 | 2020-06-25 | 10
Sample phase title block | Gas Appliances | Currently Compliant though some inspections due | Estates & Health & Safety | 1 | 100% | 2020-06-16 | 2020-06-25 | 10
| Electrical Installations/ Equipment | Currently Compliant though some inspections due | Estates & Health & Safety | 1 | 100% | 2020-06-16 | 2020-06-25 | 10
| Test building emergency systems: lights, fire, pool, security | Currently Compliant though some inspections due | Estates & Health & Safety | 1 | 100% | 2020-06-16 | 2020-06-25 | 10
| Complete all appropriate risk assessments and safe systems of work to provide a safe environment for both staff and customers alike |  | Estates & Health & Safety | 1 | 60% | 2020-06-16 | 2020-06-25
| Car Parking Facilities | Presently there is no requirement to mark out social distance arrangements within our car parking facilities | Estates & Health & Safety | 2 | 100% | 2020-06-16 | 2020-06-25
HR Phase - STAFF ENGAGEMENT
| Protect Staff - PPE | Ensure all staff are appropriately trained and equipped to deal with social distancing from customers ensure we provide them a safe working environment at all costs. | Ops and HR | 1 | 80% | 2020-06-08 | 2020-06-24 | 17
| Each facilitate will operate with a dedicated team of NL leisure that will fulfil the duties of managing and delivering the program in a safe and friendly controlled environment. Identified staff to be removed from furlogh. Progress with removing agreed staff from furlough depending on venue and service delivery requirements | C&LNL policy requires 7-10 days notice: • 1 x Duty Manager • 1 x Supervisor • 1 x Reception • 1 x Cleaner • 2 x Leisure Attendant • 6 x Coaches | HR | 1 | 100% | 2020-06-08 | 2020-06-25 | 18
| Identify staffing and customer communication strategy |  | Marketing | 1 | 90% | 2020-06-08 | 2020-06-25 | 18
| Identify staffing COVID-19 Training Plan | To ensure that all staff training is up to date, Ensure all staff are appropriately trained and equipped to deal with social distancing, managing conflict PPE and we are relevant the use of machinery/Gator. ensure we provide staff with knowledge to work in a safe environment. | Operations | 1 | 100% | 2020-06-08 | 2020-06-25 | 18
| Identify staffing resource plan to deliver all tasks within Phase 1 | Influenced by furlough and sheilding staff | Ops and HR | 1 | 100% | 2020-06-08 | 2020-06-25 | 18
The cell to the right contains the phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new title in the cell to the right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data according to cell A9’s instructions. Update the phase details in the cell to the right based on cell A8’s instructions. Continue navigating down column A cells to learn more. If you haven’t added any new rows in this worksheet, you will find that two additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through the column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Contact all members of staff to arrange shift patterns | Determine those that still need to self due to quarantine due to pre existing medical conditions and how this will impact of shift cover. Staff shall be recruited from employees currently on furlough and requires 7 days’ notice of return to work date, to be given in writing. As we can only furlough staff for a minimum of 3 weeks at any one time plan would be for employees working one on and 3 weeks off, so allowing furlough in between. | Ops and HR | 1 | 100% | 2020-06-08 | 2020-06-25 | 18
The cell to the right contains the phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new title in the cell to the right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data according to cell A9’s instructions. Update the phase details in the cell to the right based on cell A8’s instructions. Continue navigating down column A cells to learn more. If you haven’t added any new rows in this worksheet, you will find that two additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through the column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Liaise and communicate the recovery plan and any HR implications to the respective unions | JCC | Ops and HR | 1 | 20% | 2020-06-08 | 2020-06-25 | 18
The cell to the right contains the phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new title in the cell to the right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data according to cell A9’s instructions. Update the phase details in the cell to the right based on cell A8’s instructions. Continue navigating down column A cells to learn more. If you haven’t added any new rows in this worksheet, you will find that two additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through the column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Provide safe staff welfare facilities and compliance with current social distancing guidelines | Workplace staff rooms must be closed unless there are no practical alternatives in terms of providing food for staff or space for breaks. Staff should be encouraged to bring their own food and minimise the number of people there are at any one time via rotors, so as to comply with social distancing rules. Do not provide communal kitchen items, such as mugs or cutlery, staff are to bring their own and wash them at home each day. When and if practical to do so, staff should take designated brakes outside the building or even in their own cars. | Ops and HR | 1 | 50% | 2020-06-08 | 2020-06-25 | 18
SPORTS DEVELOPMENT: Activity Delivery
| Ensure all staff are aware of the safe customer journey and actively manage any pre-identified potential two meter hotspots / crossovers | Ensure staff and customers keep safe social distancing from customers and each other, floor markings, sign posts etc. Customer confidence will be key therefore effective customer communication and marketing strategy should be used. | Operations | 1 | 80% | 2020-05-08 | 2020-06-25 | 49
| Develop a detailed program activity plan/timetable to be delivered across all respective Hubs. | To increase the variety of sports and activities on offer at the community hubs, a number of sport specific programmes would be available and rotated around the hubs each week for the children to take part in. This will include football and dance. | Sports development | 1 | 90% | 2020-06-11 | 2020-06-25 | 15
| Ensure that adequate provision of sports and additional equipment necessary for a high-quality delivery | CLNL will also be able to provide additional sports equipment to enhance the quality of sporting activities in the community hubs. These are detailed below; 1. Street Soccer Portable Football Pitch i. The portable pitch could be set up in the playground of the hub and used by small groups at a time. 2. Smoothie Bike i. The smoothie bike is a great tool to use to teach children of healthy eating and lifestyles. 3. Balanceability bikes/helmets i. The balance bikes could be used in the outdoor or indoor areas and is aimed at children aged 2-7 years of age to teach them valuable basic cycling skills. This could therefore be used in the nursery section of the hubs as well as the primary section. | Sports development | 1 | 100% | 2020-06-11 | 2020-06-25 | 15
| Establish and train staff and appropriate sanitisation of any equipment | Equipment can be used on a rotational basis at all community hubs across North Lanarkshire and all staff will ensure that the equipment is cleaned after use and also used safely. | Sports development | 1 | 80% | 2020-06-11 | 2020-06-25 | 15
| Reduce activity/class participation numbers | Develop activity lesson plans to accommodate a 1 to 6 ratio | Sports development | 1 | 100% | 2020-06-11 | 2020-06-25 | 15
| Avoid congestion points within venues | Stagger other activity start and finishing times/welfare breaks,/lunch to avoid multiple gatherings or any congestion points. | Sports development | 1 | 80% | 2020-06-11 | 2020-06-25 | 15
| Activity/lesson plans should be devised to deliver an outdoor environment | When and if safe and practical to do so, activities should be delivered in an outdoor environment in the first instance. Appropriate risk assessments must be completed before hand. | Sports development | 1 | 100% | 2020-06-11 | 2020-06-25 | 15
| The recommended two meter social distancing guidance should be applied in all instances | All activity areas should be adapted to accommodate safe social distance protocols | Sports development | 1 | 100% | 2020-06-11 | 2020-06-25 | 15
| Staff and participants should be encouraged to wear face masks we are practical to do so | All staff will be provided with appropriate PPE face masks | Sports development | 1 | 100% | 2020-06-11 | 2020-06-25 | 15
| Everyone should be aware of mental well-being of staff and customers/children | Staff should be prepared for all emotions associated with the COVID-19 managed environment and require carefully managing by all staff/coaches who themselves may be adversely affected. Well-being is paramount. | Sports development | 1 | 80% | 2020-06-11 | 2020-06-25 | 15
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
Formulas:
START = [START, row above]
START = [END]-14
END = [START]+7
END = [START]